## Slide 1: Intramural Sports App
Roadmap
Notes: Intro:

## Slide 2: On-device Team Data Storage (Persistent storage)
Primary responsibility: Peter Dranishnikov
Duration to completion: 3-5 weeks
Tasks
  Identify data that needs to be stored locally, surviving the termination of the app
  Determine relevant data types, structures, access times, and API(s)
  Program
Notes: Peter Dranishnikov

## Slide 3: Team Data Platform sync (Web Services)
Primary responsibility: Gervonte Fowler
Duration to completion: 3 to 5 weeks
Tasks
  Choose a free web service that can efficiently handle databases.
  Create a database that can store future user information
  Interface with the app.
Notes: Gervonte

## Slide 4: Recreation Area map (Location services)
Primary responsibility: Jordan Gilpin
  Karun Mackoon
Duration to completion: 3-4 weeks
Tasks
  Conduct research regarding Location Services
  Writing code that will enable our users to log their location once they arrive on the Recreation Field or Basketball Courts using a Geofence
  Develop interactive features for the in-app map that will allow users to pick a spot on the map for trainings, team meetings, etc.
Notes: Jordan is presenting this slide

## Slide 5: User Interface
Primary responsibility: Marckenrold Cadet
  Other members
Duration to completion: Project length
Tasks
  Design the front-end of the application
Notes: Marckenrold

## Slide 6: Approach to accomplishing tasks
In order to make sure that no team members are falling behind we will be approaching each task with a waterfall technique
This means that we will split the group in 2 and approach 2 separate tasks at one time
This will allow all members of the group to gain experience in with each task
To correctly implement this our group will be communicating constantly to make sure that everyone is on the same page
Notes: Karuns presenting this slide

## Slide 7: Roadmap
Task | 3/4 | 3/11 | 3/18 | 3/25 | 4/1 | 4/8 | 4/15 | 4/22
Persistent Storage | START | >>>>> | >>>>> | DONE |  |  |  | 
Web Services Server |  | START | >>>>> | DONE |  |  |  | 
Web Services Client |  |  |  | START | DONE |  |  | 
User presence, Location |  | START | >>>>> | DONE |  |  |  | 
Checkin, Location |  |  |  | START | >>>>> | DONE |  | 
UI | START | >>>>> | >>>>> | >>>>> | >>>>> | >>>>> | DONE | 
Testing |  |  | START | >>>>> | >>>>> | >>>>> | DONE | 
Weekly Deliverables |  | x | x | x | x | x |  | 
Final Report and Presentation |  |  |  |  |  |  | Start | DONE
Notes: Presenter: